## 客户需求
节点：
内销车原则上属于销售车，按照Conti流程，销售车需满足PPAP & PSW签署，需过MLC70。
Product MLC70：2月1日
Product MLC60：1月29日
domain MLC60：1月28日

## System
Xu-EXT, Brandon
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | Have all the actions from the previous MLC Release been clarified and closed? | requirement link work have not been done till now, need each compitency include system, sofware, ohardware, test engineer to work on that, need one month work. |  |  | need each compitency include system, sofware, hardware, test engineer to work on that, need one month work. | 2023-02-24
2 | Are the System requirements relevant for this MLC release agreed and linked? | system requirement all agreed, link work ongoing, need team to link on DOORS. |  |  | need each compitency include system, sofware, hardware, test engineer to work on that, need one month work. | 2023-02-24
3 | Are the System requirements relevant for this MLC release agreed and linked? | Software and function have been tested, and bugs need to be fixed before MLC70 |  |  | Software and function have been tested, and bugs need to be fixed before MLC70
4 | Are the technical risks identified, analyzed, treated and monitored in the risk action list and acceptable for the corresponding MLC phase? | Requirement have been clarified, only need link in DOORS
5
6
7
8
9
10
11
12

## FS
lu guangwei
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | FSM2 Red |  |  | High
2 | FSM PV Yellow |  |  | High
3
4
5
6
7
8
9
10
11
12

## CS
li zehua
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | （e-Sign已完成签署）
2
3
4
5
6
7
8
9
10
11
12

## ME
xie yujie
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | （可预见范围内，无风险）
2
3
4
5
6
7
8
9
10
11
12

## HW
Yuan Ganggang
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | （可预见范围内，无风险）
2
3
4
5
6
7
8
9
10
11
12

## ST
Yuan Ganggang
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | （可预见范围内，无风险）
2
3
4
5
6
7
8
9
10
11
12

## SW
BSW：Zhang jin03
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | OTA需求可能变更，有新开发可能； |  |  | High | OTA需求需系统尽快确认
2 | 功能安全未移植 |  |  | Low
3 | 截至1/11，底软还有5 bug未修复； |  |  | Medium
4
5
6
BSP：Zhang Wei12
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | ADR：完成度约85%，依赖于CAN总线采集数据。 |  |  | Medium | 需系统澄清
2
3
4
5
6
功能：Ling Yun03
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1
2
3
4
5
6
7
8
9
10
11
12

## TVLE
shi jingyue
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1
2
3
4
5
6
7
8
9
10
11
12

## EBOM
Yu Chong02
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1 | （可预见范围内，无风险）
2
3
4
5
6
7
8
9
10
11
12

## MLC60_65
Domain | NOK item | Action | Due Date | Responsible
System |  |  | 2023/01/27 | Xu-EXT, Brandon
FS | FSM for PV德国的评审结果黄灯。 (same with C385) |  | 2023/01/27 | lu guangwei
CS | 1.当前信息安全方案德国评审未通过，涉及三大风险点：隐私法规，产品可靠性和IP保护 2.隐私法规和产品可靠性 esign 11.16已完成 3. IP保护12.02前完成IP保护风险接受的esign 12.05已经完成 (same with C385) | 隐私法规和产品可靠性e-Sign ID：15200597； IP保护e-Sign ID：15295898。 | 2023/01/27 | li zehua
HW(EE) |  |  | 2023/01/27 | yuan Ganggang
ME |  |  | 2023/01/27 | xie yujie
ST |  |  | 2023/01/27 | yuan Ganggang
SW |  | 全功能&80%性能&具备上公共道路条件 确定一版软件带AEB，释放给客户时需关闭（或减速度为0），可以无FOT，没有集成功能安全，且获得客户认可。确定做测试时间（建议1/15）。 项目组正式发邮件出来，说明可以用于MLC60&65， --- Luo xiaobo/yu chong02/zhang jin03 --12/29 12/30：以1/3日释放的软件作为过MLC60&65的软件。 | 2023/01/27 | zhang jin03 & Zhang, Qihang02
TVLE |  | 报告出来后才有，预计1/15---gu yanjun02 | 2023/01/27 | shi jingyue
EBOM |  |  | 2023/01/27 | yu chong02
Product |  |  | 2023/01/29 | yu chong02

## template
No. | Quesiton | Answer | Gap | Risk level | Action | Due Date
1
2
3
4
5
6
7
8
9
10
11
12